## ProjectSchedule
ULTRACONTACTS.COM
Group 22 |  | Project Start: | 2020-05-12
|  | Today: | 2020-06-01
|  | Display Week: | 1 |  |  | 2020-05-11 | [6 empty] | 2020-05-18 | [6 empty] | 2020-05-25 | [6 empty] | 2020-06-01 | [6 empty] | 2020-06-08 | [6 empty] | 2020-06-15 | [6 empty] | 2020-06-22 | [6 empty] | 2020-06-29
 | time axis 2020-05-11 to 2020-07-05
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2020-05-11 to 2020-07-05
Documentation
Gantt Chart | Cade | 100% | 2020-05-19 | 2020-05-31 | 13
Trello | Cade | 100% | 2020-05-19 | 2020-05-31 | 13
Powerpoint | Cade | 100% | 2020-05-25 | 2020-05-31 | 7
ERD | David | 100% | 2020-05-22 | 2020-05-31 | 10
Database
Setting up Server | David | 100% | 2020-05-14 | 2020-05-15 | 2
Creating Database | Cade | 100% | 2020-05-15 | 2020-05-15 | 1
Scheming Design | David & Cade | 100% | 2020-05-15 | 2020-05-18 | 4
Creating Tables | David | 100% | 2020-05-16 | 2020-05-18 | 3
Task 5 |  |  | 2019-01-18 | 2019-01-21 | 4
API
Contact Editing | Mirette & Jack | 100% | 2020-05-16 | 2020-05-21 | 6
Authentication | Mirette & Jack | 100% | 2020-05-18 | 2020-05-31 | 14
Signup/Create/Delete php | Mirette | 100% | 2020-05-18 | 2020-05-21
Search/Update php | Jack | 100% | 2020-05-18 | 2020-05-22
Design
Backend Design | Daneil & Gasper | 100% | 2020-05-18 | 2020-05-31 | 14
Front End/Framework | Daneil & Gasper | 100% | 2020-05-18 | 2020-05-31 | 14
Connecting to API | Daneil & Gasper | 100% | 2020-05-26 | 2020-05-27 | 2
Front End/Framework
Setup | Daneil & Gasper | 100% | 2020-05-18 | 2020-05-19 | 2
Login/ CreateContacts | Gasper | 100% | 2020-05-19 | 2020-05-23 | 5
Homepage | Daneil & Gasper | 100% | 2020-05-22 | 2020-05-26 | 5
Signup/Search | Daneil | 100% | 2020-05-19 | 2020-05-24 | 6
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.